## Sheet1
Project Name: |  |  | Project Date:
When | Done | Task | Responsibility
|  |  | Crew Leader | PCTA | USFS | Lead Packer
3+ months prior |  | Identify project location and alternate location(s)
Develop project description
Ensure volunteer agreements are in place, communicate with all partners whose agreement is in place
Establish crew leader/co-leader/support roles, designate lead packer
Begin recruiting volunteers
Contact lead packer for pack stock availability and authorize packers
1-2 months prior |  | Reserve/secure campsite locations
Address access issues (locked gates, 4wd roads, etc.)
Designate additional volunteers necessary (camp cook, etc.)
Scout project
Assess trail head access for parking, stock trailers and stock facilities
Continue volunteer recruitment
2-3 weeks prior |  | Finalize trip details with PCTA, agency staff, and packers
Contact lead packer to confirm number of pack stock needed, times, trail head, camp location, road conditions, volunteer application, radio/cell phone use, tool carriers, bear boxes, buckets, load weights, alternate plans, specialty loads, gear prep, loading and pack-in expectations
Continue volunteer recruitment
1 week prior |  | Complete and distribute TCP to crew leaders, lead packer, supervisors and dispatch
Contact volunteers (introductions, meeting time/place, what to bring, weather, travel details, food requests, etc). Send copy to: co-leaders, packers, supervisors, and vol. coordinator
Obtain all access items necessary (keys, parking passes, camp passes, etc.)
Gather tools, kitchen, camp gear, radios. Organize, clean and ensure functioning.
Notes:
Days before trip |  | Confirm details with supervisors and vol. coordinator
Confirm project, trailhead, and pack-in load with lead packer
Crew Leader and Lead Packer discuss and confirm pack-in logistics
Print paperwork (volunteer profiles, TSS, EAP, JHAs, sign-in sheet, etc.)
Note specific volunteer needs or concerns
Complete menu and food shopping
Contact packer to re-confirm number of pack stock needed and project details
Organize food and weigh bags (if necessary for packing)
First day of trip |  | Complete Tailgate Safety Session (TSS) with entire crew including packers
Ensure all sign-in and sign appropriate JHA including packers
Lay out organized food, tools, and gear. Assist packer(s) with loading
Ensure safe and productive working environment (throughout)
At camp help packer(s) unload, confirm number of stock required for move out, re-confirm date and time.
At camp discuss LNT, camp, hygiene, chores and cooking routine
After trip |  | Pack tools, kitchen and camp gear for loading on pack stock
Help packer(s) load and unload after returning to trail head
Call supervisor to update
Submit project report to supervisors, PCTA, and agency. Upload photos.
Send thank you email to volunteers
Clean, repair, return tools, kitchen and camp gear
Notes: